## Form SCMP 7.5a Rev C
SCMP Form 7.5 (a) WT Package Analysis - Complete prior to approval as part of developing the work transfer project
Considerations Applicable to all Work Transfers
| Process | Yes/No | Triumph WT Potential Actions(s) | Base Acceptability | Comments
1 | Has the Sourcing Project Preliminary Checklist SCMP 7.4 (a) been completed? | Answer | Formally request completion of SCMP 7.4 (a) | Confirm Sourcing Project Preliminary Checklist SCMP 7.4 (a) complete | May request a hold on the work transfer if SCMP 7.4 (a) not complete
2 | Have all open actions from SCMP 7.4 review been satisfactorily closed or will be transfered to SCMP 7.5 (f) | Answer | Work with sourcing project lead to transfer open actions | Confirm actions have been transferred to SCMP 7.5 (f)
| Potential New Source(s) | Yes/No | Triumph WT Potential Actions(s) | Base Acceptability | Comments
3 | Is there a history of non-conformance at current source or of similar parts at proposed source(s)? | Answer | Consult site quality for instances of non-conformance | Confirm non-conformances have completed RCCA
4 | Do the sources have quality management systems that meet Site requirements? | Answer | Confirm supplier is on the site AVL and obtain a copy of AS9100 or ISO accreditation | Confirmation supplier is on site AVL
| Product | Yes/No | Triumph WT Potential Actions(s) | Base Acceptability | Comments
5 | Have the parts included in this transfer been reviewed to determine if they are included on an existing work transfer or projected to be awarded to a supplier with other active transitions ? | Answer | Confirm parts are not included in another work transfer - or if they are confirm with site sourcing that this is still a valid work transfer | Confirmation from site to show validity of transfer | This could be a dual sourcing initiative
6 | Is the transition part flight safety/flight critical? | Answer | Confirm with Engineering | Confirm potnetial sources can produce Flight Critical Parts
| Resources | Yes/No | Triumph WT Potential Actions(s) | Base Acceptability | Comments
7 | Are there any travel concerns specific to this project? | Answer | Are any of the suppliers in a location that is on a "no travel" list (Official or Triumph) | Confirmation that potential suppliers are not on a "no travel" list
8 | Has Supplier Development been consulted to affirm supplier(s) performance / risk? | Answer | Review potnetial suppliers wit hSupplier Development | Document Supplier Development identified performance/risk (if applicable)
Yes
No
Answer