## 7.5(b) Prelim. Assessment
SCMP Form 7.5 (b) Preliminary Risk Assessment - Complete prior to approval as part of developing the work transfer project strategy
Considerations Applicable to all Work Transfers- Any non-addressable item must be moved to Project Risk Assessment
Project Classification
Passport | Potential New Source(s) | Yes / No | Suggested Actions | Specific Action | Comments
I | Will the transition affect another Triumph Group Business Unit? | Yes | Confirm via Cost Management Project Tracker if selected supplier is on any other active projects or if the transition will impact existing supplier relationship.
I | Is the capability to produce the part(s) within the suppliers capabilities? | Yes | Confirm if a validated SCMP 3.3 is in existance, if not schedule with Supplier Development to perform an SCMP 3.3.
I | Do the supplier(s) have the capacity available to accommodate transfer? | No | Coordinate Capacity Study with sources.
I | Do the sources have an existing contract with Triumph Group with acceptable terms and conditions or are they willing to enter into an agreement with Triumph Group on acceptable Terms & Conditions? | No | Contact Supply Chain Management Contract Specialist to Verify when/if an agreement will be executed
I | Are the sub-tier suppliers to the current source critical to the process or part? | Yes | Verify sub-tier supplier management capabilities.
I | Is the current source a Small-Disadvantaged, Woman-owned, or Veteran-owned Business? | Yes | Review with SBLO and/or Contracts team.
I | Are there any offset / Industrialization requirements or contractual requirements that affect this transfer? | Yes | Review with Contracts team.
| Could the current source's performance affect this transition? | Yes | Develop mitigation plan for poor performance to be reflected in overlap plan.
| Are there any EH&S factors to be considered as part of this work transfer (e.g. materials of concern, EHS controls at the new source, liability concerns)? | Yes | Formally address concerns with Triumph Group EHS.
Passport | Raw Materials and Sub-tier Management | Yes/No | Suggested Actions | Specific Action | Comments
I | Is the raw material that is currently used available to the potential new sources? | No | Identify approved source for material and secure forecast to support the transfer.
I | Does the current source provide a product containing exotic materials (difficult to obtain, or needs to be procured in large volumes) or proprietary material (patented or controlled by a single manufacturer)? | Yes | Identify raw material requirements, long lead time items and bridge planning & special qualification testing requirements.
I | Does the raw material for the potential new sources require an export license? | Yes | Obtain export license.
Passport | Product | Yes / No | Suggested Actions | Specific Action | Comments
I | Does the manufacture of the part have any processes or assembly methods that are Triumph Group and/or customer controlled. | Yes | Provide training/documents to supplier/obtain Customer approvals as required.
I | Are there any customer requirements / Flow Downs that must be provided to the potential new sources? | Yes | Ensure Customer requirements hav been identified and will be part of the quote as applicable. Re: Customer Compliance Matrix
I | Are there engineering or quality documents in place that supplement the drawing pack? (permits, concessions, deviation requests, in process ECNs, rework drawings, customer assertions) | Yes | Ensure the drawing pack can stand on its own. Consider video or operator/routing interviews, auditing work instructions against actual process.
| Will the change of source of supply require requalification of the part or end-assembly? | Yes | Review & plan for requalification requirements. Create and approve qualification plan.
| Does the part have specific FAA, EASA, or DOD certification requirements that will require certification of the new supplier or TGI manufacturing facility? | Yes | Review & plan for qualification requirements for new supplier / manufacturing facility. Ensure all types of manufacturing processes (OEM, PMA, DER) are mapped to identify and supplement any gaps.
| Will the move of this product require any language translation of documentation (e.g. specs, drawings, work instructions) | Yes | Establish plan for language conversion and validation.
| Will the move of this product require any measurement conversions (e.g. english to metric) | Yes | Establish plan for measurement conversion and validation.
Passport | Tooling & Equipment | Yes / No | Suggested Actions | Specific Action | Comments
I | Is there any Triumph Group owned tooling, test and/or manufacturing equipment involved in transfer? | Yes | Work with BD to Review Contract. Determine financial impact & CapEx req'ts. Review tooling condition and perform tooling validation (ie last article, laser inspection of the tool or internal review of production parts). Address export requirements.
I | Is there any Customer owned tooling, test and/or manufacturing equipment involved in transfer? | Yes | Work with BD to Review Contract. Determine financial impact & CapEx req'ts. Review tooling condition and perform tooling validation (ie last article, laser inspection of the tool or internal review of production parts). Address export requirements.
I | Does the current source have source-owned tooling, test and/or manufacturing equipment? | Yes | Work with BD to Review Contract. Determine financial impact & CapEx req'ts. Review tooling condition and perform tooling validation (ie last article, laser inspection of the tool or internal review of production parts). Address export requirements.
Phase | Resources | Yes / No | Suggested Actions | Specific Action | Comments
I | Is a communication plan required? (e.g. channels, tools - Obeyas, frequencies) | Yes | Establish communication plan as required with internal and external stakeholders including internal Customers.
I | Have the preliminary personnel requirements/team membership been established for this project? | No | Determine preliminary, dedicated personnel requirements & staffing plan including functional SME's.
Yes
No
N/A