## Instructions
Automated FAFP Quick Start Guide
This spreadsheet uses formulas and conditional formatting to minimize the effort required to generate a First Article Flow Plan and the associated Transition Project Metrics
The keys steps to generating a FAFP are as follows:
1 | Populate the header with details regarding the transition
2 | Add the transition part details to the spreadsheet….
3 | Input Plan dates to each manufacturing step (these are the original plan dates and are not to be modified)
4 | Input Revised Plan date only if a deviation from the original plan date is needed
5 | Input Actual date when manufacturing step was completed
6 | Including the required On-Dock Date
Both the plan dates and actual dates are conditionally formatted as follows:
Plan dates that greater than 2 weeks in the future are filled green
Plan dates that are withing 2 weeks of the due date are filled yellow
Plan dates that are older than today's date are filled red
Actual dates that are not older than the plan date are filled green
Actual dates that are less than 5 days late to the plan date are filled yellow
Actual dates that greater than 5 days late to the plan date are filled red
The data on the Stop Light report is populated using data from the FAFP with the following exceptions:
1 | Day and time of the transition team meetings
2 | Date and status update
3 | Production assessment (if applicable)
4 | Overall transition and production line status (see definitions below)
Overall Transition Status - Covers the status of the overall transition.
Green - things going according to plan
Yellow - There is potential risk to plan
Red - Project is behind schedule or at risk
Transition manager will rate the overall project accordingly.
Production Line Status – Indicates whether or not the production requirements to the customer are being met or missed.
Green - production requirements are being met
Yellow - potential risk in not supporting production requirements
Red - Missed production line schedules
See the Transition Playbook for detailed step-by-step instructions and definitions.
Templates are provided to help generate the FAI and Tooling Transfer graphs.
The process is the same for both graphs. You can generate a graph in three steps:
1 | Entering the earliest and latest estimated completion/deliveries.
The spreadsheet will auto-scale the graph into 20 periods.
2 | Enter the baseline estimate for completion of the FAIs/Tool Transfers
3 | Enter the actual completed FAIs/Tool Transfers
Data needs to be entered as a cummulative total ramping up from 0 to the total
The 'Transition Team RACI' template the the 'Data Transmittal Checklist' template are included in this file
to allow Transition Project Managers to house all pertinent documents in a single file.
1
1
2
6
2
1
3
4
1
2
3
Unhide columns to add up to 15 key manufacturing steps
3
4
5

## First Article Flow Plan
First Article Flow Plan | [77 empty] | Holidays Excluded
Receiving Supplier: |  |  |  | TGI Companies Transitioning Parts:
Transition Package: |  |  |  | TGI Transition Project Manager:
Last Updated by: |  | Name of Person |  | TGI Buyer:
Date of Last Update: |  | Date of Update |  | Sending Supplier:
Today's Date |  | 2022-08-22
CMPT WT Project # |  | ABC
|  |  |  | Supplier Lead Time Blow-Back (M-Days) | [6 empty] | 0 |  |  | 30 |  |  | 0 |  |  | 10 |  |  | 10 |  |  | 5 |  |  | 0 |  |  | 10 |  |  | 2 |  |  | 3 |  |  | 2 |  |  | 15 |  |  | 0 |  |  | 2 |  |  | 4 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 4 |  |  | 3 |  |  | 2 | [6 empty] | 43976
[5 empty] | % COMPLETE |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
[5 empty] | COMPLETE |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[5 empty] | BALANCE DUE |  |  | 20 |  |  | 40 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20
Item Number | Assembly/Part Number | Dash Rolls | Part Description | Section (Next Higher Assy) | Program | Site | # Per Ship | PO Placed | PO | PO Item | Engr Data Received |  |  | Material Ordered |  |  | Material DOD |  |  | NC Tool Design |  |  | NC Program |  |  | Planning |  |  | Issue Material & Realease WO |  |  | Tool FAB |  |  | Machine Start/Rough |  |  | Machine Finish |  |  | Inspect |  |  | Outside Processing Out |  |  | Outside Processing Rcv |  |  | ID |  |  | Detail Net-Inspect Submit |  |  | Detail FAI |  |  | Assembly Start |  |  | Assembly Finish |  |  | Assy Net-Inspect Submit |  |  | Assembly FAI |  |  | PKG/Ship |  |  | PO On Dock Date |  |  | Comments
[11 empty] | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Commit Date | Actual
1 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
2 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
3 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
4 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
5 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
6 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
7 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
8 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
9 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
10 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
11 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
12 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
13 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
14 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
15 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
16 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
17 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
18 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
19 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
20 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
Formulas:
Engr Data Received = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Material Ordered],WORKDAY([Material Ordered],-L9,CI2:CI19))
Material Ordered = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Material DOD],WORKDAY([Material DOD],-O9,CI2:CI19))
Material DOD = IF(ISNUMBER(SEARCH("N/A",[Actual])),[NC Tool Design],WORKDAY([NC Tool Design],-R9,CI2:CI19))
NC Tool Design = IF(ISNUMBER(SEARCH("N/A",[Actual])),[NC Program],WORKDAY([NC Program],-U9,CI2:CI19))
NC Program = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Planning],WORKDAY([Planning],-X9,CI2:CI19))
Planning = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Issue Material & Realease WO],WORKDAY([Issue Material & Realease WO],-AA9,CI2:CI19))
Issue Material & Realease WO = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Tool FAB],WORKDAY([Tool FAB],-AD9,CI2:CI19))
Tool FAB = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Machine Start/Rough],WORKDAY([Machine Start/Rough],-AG9,CI2:CI19))
Machine Start/Rough = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Machine Finish],WORKDAY([Machine Finish],-AJ9,CI2:CI19))
Machine Finish = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Inspect],WORKDAY([Inspect],-AM9,CI2:CI19))
Inspect = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Outside Processing Out],WORKDAY([Outside Processing Out],-AP9,CI2:CI19))
Outside Processing Out = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Outside Processing Rcv],WORKDAY([Outside Processing Rcv],-AS9,CI2:CI19))
Outside Processing Rcv = IF(ISNUMBER(SEARCH("N/A",[Actual])),[ID],WORKDAY([ID],-AV9,CI2:CI19))
ID = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Detail Net-Inspect Submit],WORKDAY([Detail Net-Inspect Submit],-AY9,CI2:CI19))
Detail Net-Inspect Submit = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Detail FAI],WORKDAY([Detail FAI],-BB9,CI2:CI19))
Detail FAI = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Assembly Start],WORKDAY([Assembly Start],-BE9,CI2:CI19))
Assembly Start = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Assembly Finish],WORKDAY([Assembly Finish],-BH9,CI2:CI19))
Assembly Finish = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Assy Net-Inspect Submit],WORKDAY([Assy Net-Inspect Submit],-BK9,CI2:CI19))
Assy Net-Inspect Submit = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Assembly FAI],WORKDAY([Assembly FAI],-BN9,CI2:CI19))
Assembly FAI = IF(ISNUMBER(SEARCH("N/A",[Actual])),[PKG/Ship],WORKDAY([PKG/Ship],-BQ9,CI2:CI19))
PKG/Ship = IF(ISNUMBER(SEARCH("N/A",[Actual])),[PO On Dock Date],WORKDAY([PO On Dock Date],-BT9,CI2:CI19))

## Action Log
LEGEND
Priority | Description | Time to close | Status | Description
1 | CRITICAL action requires highest level of attention | within 1 business day | Past Due | Action item is past due date
2 | URGENT action - must hold schedule | within 2 business days | Next Day | Action is due next day
3 | IMPORTANT action | within a week | At Risk | Action is at risk to not complete on-time
4 | WORKING action | more than 1 week | Open | Action is open and on schedule
|  | Revision: | 2022-08-22 |  |  |  |  | Past Due | Open | Closed
--- Action Tracker |  |  | Supplier/Package |  |  |  |  | 0 | 0 | 0
Item | Program | Category | Action | Priority | Site | Responsible | Initiation Date | Date Due | Date Complete | Status | Comments
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## Old FAPF Plan (hidden)
|  | Person | [5 empty] | TA-VAD Team Members | [7 empty] | TS-KC Team Members | [12 empty] | TODAY = | 2022-08-22
| Last Updated by: | Jace Kline | [5 empty] | Project Lead: Joe Ragusa (972) 946-5422 | [7 empty] | Project Lead: Jace Kline (817) 529-6179
| Date: | 2022-08-22 | [5 empty] | Buyer: Brandy Gillingham (M), Monica Navarro (H), Drew Culton (S)
Tech Ops: As Needed
SQE: As Needed
Essner |  |  | 1) PO’s will be issued with a –FP suffix. 2) Parts will be delivered without -FP sufix. 3) Refer to TSSP for part identification. 4) Request correction if TSSP doesn't specivy part identification without -FP sufix.
Gray out if operation not required | [9 empty] | Lead time blow-back (M-Days) ---> | 1 | 1 | 10 | 7 | 7 | 3 | 0 | 10 | 10 | 2 | 2 | 10 | 15 | 3 | 0 | 0 |  | 3 | 2 | 7
| % COMPLETE | [6 empty] | 98.44% |  |  | 100% | 100% | 85.96% | 85.96% | 84.21% | 84.21% | 68.42% | 77.19% | 77.19% | 77.19% | 77.19% | 63.16% | 63.16% | 63.16% | 47.37% | 47.37% |  | 61.4% | 47.37% | 47.37%
| COMPLETE | [6 empty] | 63 |  |  | 57 | 57 | 49 | 49 | 48 | 48 | 39 | 44 | 44 | 44 | 44 | 36 | 36 | 36 | 27 | 27 |  | 35 | 27 | 27
| BALANCE DUE | [6 empty] | 1 |  |  | 0 | 0 | 8 | 8 | 9 | 9 | 18 | 13 | 13 | 13 | 13 | 21 | 21 | 21 | 30 | 30 |  | 22 | 30 | 30
Item Number | Part Number (PO Suffix -FP) | Dash Rolls | Part Description | Section (NHA) | Prog | Site | Qty Per Ship | PO Placed | PO | PO Item | Eng Data Received | Material | Tooling Design/Fab/Transfer | Planning | NC Program | Shear & Saw | Saw | Route/ Water Jet | Forming & Trimming | Deburr | Inspect | Heat Treat/ Age | Outside Process | Prime, Paint | Paint | Assembly | Assembly | FAI Inspect | Source Inspect | Ship Date | PO On-Dock Date | Lock Down PO "On Dock Date" | Comments | COMMENTS | Package (Ref) | Tool Status
1 | 148U3928-1 |  | STRINGER, REINFORCEMENT | 481-3-2190 | 747 | 1600 | 2 | Y | 4500051961 | 10 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | 2013-10-09 | 2013-10-09 |  | 2013-10-09 | 2013-10-14 | 2013-10-16 | 2013-10-25 | Yes | 148U3928-1 | Parts are in Final Q.A | (#3) LTA/0298/2013 | Tools at Essner
2 | 65B17373-20 |  | STRAP | 4230D/2-9070-8F | 747 | 1600 | 1 | Y | 4500052158 | 70 | C | C | C | C | C | C | C | C | C | C | C | 2013-09-06 | 2013-09-20 | 2013-10-11 | 2013-10-16 | 2013-10-16 |  | #NAME? | #NAME? | #NAME? | 2013-11-01 | Yes | 65B17373-20 | Parts are at Gamma for Heat Treat | (#9) LTA/0302/2013 | Tools at TAVAD shipping Dock
3 | 65B07491-47-01 |  | INTERCOSTAL, | 4655/9070-1 | 747 | 1300 | 1 | Y | 4500051430 | 60 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | #NAME? |  |  | C | #NAME? | #NAME? | 2013-11-01 | Yes | 65B07491-47-01 | Ready for Source/Net-inspect Approval | (#9) LTA/0302/2013 | Tools at TAVAD shipping Dock
4 | 65B07478-13 |  | STRAP | 4630R/9020-1 | 747 | 1300 | 1 | Y | 4500051430 | 50 | C | C | C | C | C | C | C | C | C | C | C | 2013-09-26 | 2013-09-20 | 2013-10-11 | 2013-10-16 | 2013-10-16 |  | #NAME? | #NAME? | #NAME? | 2013-11-01 | Yes | 65B07478-13 | Parts are at Gamma for Heat Treat | (#9) LTA/0302/2013 | Tools at TAVAD shipping Dock
5 | 65B06351-15-01 |  | ANGLE, | 4632L/7060-2 | 747 | 1300 | 1 | Y | 4500051430 | 30 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | #NAME? |  |  | C | #NAME? | #NAME? | 2013-11-01 | Yes | 65B06351-15-01 | Ready for Source/Net-inspect Approval | (#9) LTA/0302/2013 | Tools at TAVAD shipping Dock
6 | 65B26187-404 |  | SUPPORT ANGLE | 65B26187-410 | 747 | 1300 | 5 | Y | 4500051430 | 100 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | #NAME? |  |  | C | #NAME? | #NAME? | 2013-11-30 | Yes | #REF! | Ready for Source/Net-inspect Approval | (#9) LTA/0302/2013
7 | 65B26187-403 |  | SUPPORT ANGLE , | 65B26187-410 | 747 | 1300 | 5 | Y | 4500051430 | 90 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | #NAME? |  |  | C | #NAME? | #NAME? | 2013-11-30 | Yes | #REF! | Ready for Source/Net-inspect Approval | (#9) LTA/0302/2013
8 | 65B07491-48-01 |  | INTERCOSTAL, | 4640/9030-1 | 747 | 1300 | 1 | Y | 4500051430 | 70 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | #NAME? |  |  | C | #NAME? | #NAME? | 2013-11-30 | Yes | #REF! | Ready for Source/Net-inspect Approval | (#9) LTA/0302/2013
9 | 65B07174-433 |  | STIFFENER, | 4636/8070-1 | 747 | 1300 | 1 | Y | 4500051430 | 40 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | #NAME? |  |  | C | #NAME? | #NAME? | 2013-11-30 | Yes | #REF! | Ready for Source/Net-inspect Approval | (#9) LTA/0302/2013
10 | 65B04406-608 |  | WEB , | 65B04406-882-06 | 747 | 1800 | 1 | Y | 4500053392 | 10 | C | C | C | C | [8 empty] | #NAME? |  | #NAME? |  |  | #NAME? | #NAME? | #NAME? |  | Essner needs (1) FD | #REF! | MISSING TOOL 4881684-00/C00 FD - BACD2000-10 | (#9) LTA/0302/2013
12 | 185T4000-013-1000 |  | WEB, | 185T4000-183-533 | 767 Common | 1600 | 1 | Y | 4500052161 | 70 | C | C | C | C | C | C |  | C | C | C | C | 2013-10-02 | #NAME? | 2013-11-06 | #NAME? | 2013-11-11 |  | #NAME? | #NAME? | #NAME? | 2013-11-30 |  |  | Parts in Queue for Heat Treat in-house | (#9) LTA/0302/2013
13 | 185T4000-011-2000 |  | WEB, AFT T/B FIN | 185T4000-184-532 | 767 Common | 1600 | 1 | Y | 4500052161 | 60 | C | C | 2013-08-09 | 2013-08-14 | 2013-08-14 | 2013-08-23 | 2013-08-28 | 2013-08-28 | 2013-09-12 | 2013-09-26 | 2013-09-30 | 2013-10-02 | #NAME? | 2013-11-06 | #NAME? | 2013-11-11 |  | #NAME? | #NAME? | #NAME? | 2013-11-30 |  |  | Missing tools/Docs | (#9) LTA/0302/2013
14 | 185T4000-011-1000 |  | DOUBLER, FWD T/B FIN | 185T4000-183-533 | 767 Common | 1600 | 1 | Y | 4500052161 | 50 | C | C | 2013-08-09 | 2013-08-14 | 2013-08-14 | 2013-08-23 | 2013-08-28 | 2013-08-28 | 2013-09-12 | 2013-09-26 | 2013-09-30 | 2013-10-02 | #NAME? | 2013-11-06 | #NAME? | 2013-11-11 |  | #NAME? | #NAME? | #NAME? | 2013-11-30 |  |  | Missing tools/Docs | (#9) LTA/0302/2013
15 | 185T4000-009-1000 |  | WEB, | 185T4000-183-533 | 767 Common | 1600 | 1 | Y | 4500052161 | 40 | C | C | 2013-08-09 | 2013-08-14 | 2013-08-14 | 2013-08-23 | 2013-08-28 | 2013-08-28 | 2013-09-12 | 2013-09-26 | 2013-09-30 | 2013-10-02 | #NAME? | 2013-11-06 | #NAME? | 2013-11-11 |  | #NAME? | #NAME? | #NAME? | 2013-11-30 |  |  | Missing tools/Docs | (#9) LTA/0302/2013
16 | 185T4000-008-1000 |  | WEB, | 185T4000-184-532 | 767 Common | 1600 | 1 | Y | 4500052161 | 30 | C | C | 2013-08-09 | 2013-08-14 | 2013-08-14 | 2013-08-23 | 2013-08-28 | 2013-08-28 | 2013-09-12 | 2013-09-26 | 2013-09-30 | 2013-10-02 | #NAME? | 2013-11-06 | #NAME? | 2013-11-11 |  | #NAME? | #NAME? | #NAME? | 2013-11-30 |  |  | Missing tools/Docs | (#9) LTA/0302/2013
17 | 185T4000-007-1000 |  | WEB, | 185T4000-183-533 | 767 Common | 1600 | 1 | Y | 4500052161 | 20 | C | C | 2013-08-09 | 2013-08-14 | 2013-08-14 | 2013-08-23 | 2013-08-28 | 2013-08-28 | 2013-09-12 | 2013-09-26 | 2013-09-30 | 2013-10-02 | #NAME? | 2013-11-06 | #NAME? | 2013-11-11 |  | #NAME? | #NAME? | #NAME? | 2013-11-30 |  |  | Missing tools/Docs | (#9) LTA/0302/2013
18 | 174U9300-009-500 |  | SUPPORT,DORSAL FIN SEAL ASSY. | 174U9300-010-522 | 747 | 1600 | 2 | Y | 4500052158 | 50 | C | C | 2013-08-09 | 2013-08-14 | 2013-08-14 | 2013-08-23 | 2013-08-28 | 2013-08-28 | 2013-09-12 | 2013-09-26 | 2013-09-30 | 2013-10-02 | #NAME? | 2013-11-06 | #NAME? | 2013-11-11 |  | #NAME? | #NAME? | #NAME? | 2013-11-30 |  |  | Missing tools/Docs | (#9) LTA/0302/2013
19 | 173U3509-5-01 |  | WEB, RUDDER | 173U3509-1-01 | 747 | 1600 | 1 | Y | 4500052158 | 40 | C | C | 2013-08-09 | 2013-08-14 | 2013-08-14 | 2013-08-23 | 2013-08-28 | 2013-08-28 | 2013-09-12 | 2013-09-26 | 2013-09-30 | 2013-10-02 | #NAME? | 2013-11-06 | #NAME? | 2013-11-11 |  | #NAME? | #NAME? | #NAME? | 2013-11-30 |  |  | Missing tools/Docs | (#9) LTA/0302/2013
20 | 173U3507-8-01 |  | WEB, | 173U3507-1-01 | 747 | 1600 | 1 | Y | 4500052158 | 30 | C | C | 2013-08-09 | 2013-08-14 | 2013-08-14 | 2013-08-23 | 2013-08-28 | 2013-08-28 | 2013-09-12 | 2013-09-26 | 2013-09-30 | 2013-10-02 | #NAME? | 2013-11-06 | #NAME? | 2013-11-11 |  | #NAME? | #NAME? | #NAME? | 2013-11-30 |  |  | Missing tools/Docs | (#9) LTA/0302/2013
21 | 173U3502-12-01 |  | WEB, | 173U3502-11-01 | 747 | 1600 | 1 | Y | 4500052158 | 20 | C | C | C | C | C | C | 2013-08-28 | 2013-08-28 | 2013-09-12 | 2013-09-26 | 2013-09-30 | 2013-10-02 | 2013-10-16 | 2013-11-06 | 2013-11-11 | 2013-11-11 |  | 2013-11-11 | 2013-11-14 | 2013-11-18 | 2013-11-30 |  |  | Still missing tools | (#9) LTA/0302/2013
22 | 65B04693-601 |  | INNER SKIN | 2520-3-3005/PMC10 | 747 | 1800 | 1 | Y | 4500053392 | 30 | C | C | C | C | C | C | 2013-09-18 | 2013-09-18 | 2013-10-02 | 2013-10-16 | 2013-10-18 | 2013-10-22 | 2013-11-05 | 2013-11-26 | 2013-12-03 | 2013-12-03 |  | 2013-12-03 | 2013-12-06 | 2013-12-10 | 2013-12-19 | Yes | Yes- lock down date | Parts in Queue at Water jet | (#9) LTA/0302/2013
23 | 65B09684-8 |  | STRAP, | 4210L/9090-1 | 747 | 1300 | 4 | Y | 4500051430 | 80 | C | C | C | C | C | C | C | C | C | C | C | 2013-10-23 | 2013-11-06 | 2013-11-27 | 2013-12-04 | 2013-12-04 |  | 2013-12-04 | 2013-12-09 | 2013-12-11 | 2013-12-20 | Yes | Yes- lock down date | Parts are at Gamma for Heat Treat | (#9) LTA/0302/2013
24 | 65B07491-49 |  | INTERCOSTAL, FRAME | 4610D/3-9010-8F | 747 | 1600 | 1 | Y | 4500052158 | 60 | C | C | C | C | C | C |  | C | C | C | C | 2013-10-23 | 2013-11-06 | 2013-11-27 | 2013-12-04 | 2013-12-04 |  | 2013-12-04 | 2013-12-09 | 2013-12-11 | 2013-12-20 | Yes | Yes- lock down date | Parts in Queue for Heat Treat in-house | (#9) LTA/0302/2013
25 | 65B04718-601 |  | INNER SKIN | 6530-3-3005/PMC10 | 747 | 1800 | 1 | Y | 4500053392 | 50 | C | C | C | C | C | C | 2013-09-19 | 2013-09-19 | 2013-10-03 | 2013-10-17 | 2013-10-21 | 2013-10-23 | 2013-11-06 | 2013-11-27 | 2013-12-04 | 2013-12-04 |  | 2013-12-04 | 2013-12-09 | 2013-12-11 | 2013-12-20 | Yes | Yes- lock down date | Parts in Queue at Water jet | (#9) LTA/0302/2013
26 | 185T4000-013-2000 |  | WEB, | 185T4000-184-532 | 767 Common | 1600 | 1 | Y | 4500052161 | 80 | C | C | C | C | C | C |  | C | C | C | C | 2013-10-23 | 2013-11-06 | 2013-11-27 | 2013-12-04 | 2013-12-04 |  | 2013-12-04 | 2013-12-09 | 2013-12-11 | 2013-12-20 | Yes | Yes- lock down date | Parts in Queue for Heat Treat in-house | (#9) LTA/0302/2013
27 | 173U2018-024 |  | DOOR, | 173U2018-014-501 | 747 | 1600 | 2 | Y | 4500051961 | 40 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | #NAME? |  |  | C | #NAME? | #NAME? | 2013-12-20 | Yes | Yes- lock down date | Ready for Source/Net-inspect Approval | (#3) LTA/0298/2013
28 | 146U7251-7 |  | STABILIZATION, FRAME | 4610D/3-9010-8F | 747 | 1600 | 1 | Y | 4500052158 | 10 | C | C | C | C | C | C |  | C | C | C | C | 2013-10-23 | #NAME? | #NAME? | #NAME? | 2013-12-04 |  | #NAME? | #NAME? | #NAME? | 2013-12-20 | Yes | Yes- lock down date | Parts in Queue for Heat Treat in-house | (#9) LTA/0302/2013
29 | 146U5321-212 |  | ANGLE, | 4632R/7060-2 | 747 | 1300 | 1 | Y | 4500051430 | 10 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | #NAME? |  |  | C | #NAME? | #NAME? | 2013-12-20 | Yes | Yes- lock down date | Ready for Source/Net-inspect Approval | (#9) LTA/0302/2013
30 | 69B04657-1-01 |  | SHEAR PANEL, | 4631R/8040-1 | 747 | 1300 | 1 | Y | 4500051430 | 150 | C | C | C | C | C | C |  | C | C | C | C | 2013-10-23 | #NAME? | #NAME? | #NAME? | 2013-12-04 |  | #NAME? | #NAME? | #NAME? | 2013-12-20 | Yes | Yes- lock down date | Parts in Queue for Heat Treat in-house | (#9) LTA/0302/2013
31 | 185T4000-125-1000 |  | WEB, | 185T4000-184-532 | 767 Common | 1600 | 1 | Y | 4500052161 | 90 | C | C | C | C | C | C | 2013-11-15 | 2013-11-15 | 2013-12-03 | 2013-12-17 | 2013-12-19 | 2014-01-02 | #NAME? | #NAME? | #NAME? | 2014-02-12 |  | #NAME? | #NAME? | #NAME? | 2014-02-28 | Yes | Yes- lock down date | Parts in Queue at Water jet | (#9) LTA/0302/2013
11 | 65B04241-55 |  | CHANNEL | 65B04241-410 | 747 | 1300 | 1 | Y | 4500051430 | 20 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes | #REF! | Shipped Complete | (#9) LTA/0302/2013
32 | 180T3250-011 |  | RAIN GUTTER, | 180T3250-009 | 767 Common | 1600 | 6 | Y | 4500052161 | 10 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes | 180T3250-011 | Shipped Complete | (#9) LTA/0302/2013
33 | 100T1481-033 |  | TAPER FILLER, | 145T9999-2200-010 | 767 | 1800 | 1 | Y | 4500053417 | 70 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
34 | 100T1481-026 |  | FILLER, | 145T9999-2200-010 | 767 | 1800 | 1 | Y | 4500053417 | 50 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
35 | 145T8760-143 | On PR w/QFI????? | FILLER TAPERED | 145T8907-812 | 767 | 1800 | 8 | Y | 4500053424 | 250 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
36 | 145T8760-137 |  | FILLER TAPERED | 145T8760-803-010 | 767 | 1800 | 2 | Y | 4500053424 | 230 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
37 | 145T8760-134 |  | FILLER TAPERED | 145T8796-801-002 | 767 | 1800 | 1 | Y | 4500053424 | 210 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
38 | 145T8760-133 |  | FILLER-TAPERED | 145T8798-852 | 767 | 1800 | 12 | Y | 4500053424 | 190 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
39 | 145T8760-130 |  | FILLER-TAPERED , | 145T8760-807 | 767 | 1800 | 2 | Y | 4500053424 | 170 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
40 | 145T8721-026 |  | FILLER | 145T8721-864 | 767 | 1800 | 2 | Y | 4500053424 | 150 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
41 | 145T8721-014 |  | FILLER TAPERED | 145T8721-864 | 767 | 1800 | 4 | Y | 4500053424 | 130 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
42 | 145T2620-016 |  | FILLER | 145T2620-853-010 | 767 | 1800 | 1 | Y | 4500053424 | 110 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
43 | 145T2618-006 |  | SHIM, | 145T2620-851-003 | 767 | 1800 | 4 | Y | 4500053424 | 70 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
44 | 145T2618-002 |  | SHIM | 145T2620-853-010 | 767 | 1800 | 4 | Y | 4500053424 | 10 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
45 | 100T1481-020 |  | FILLER | 145T9999-2200-010 | 767 | 1800 | 4 | Y | 4500053417 | 30 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
46 | 100T1481-019 |  | FILLER | 145T9999-2200-010 | 767 | 1800 | 4 | Y | 4500053417 | 10 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
47 | 182U0008-006 |  | SHIM, TAPERED | 906C2-813KIT | 747 | 1600 | 1 | Y | 4500051961 | 60 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes | 182U0008-006 | Shipped Complete | (#3) LTA/0298/2013 | Tools at Essner
48 | 182T0100-025 |  | SHIM, (UD) | 182T3100-005-521 | 767 Common | 1600 | 22 | Y | 4500051963 | 20 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes | 182T0100-025 | Shipped Complete | (#3) LTA/0298/2013 | Tools at Essner
49 | 182T0100-024 |  | SHIM, (UD) | 182T4000-005-521 | 767 Common | 1600 | 22 | Y | 4500051963 | 10 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes | 182T0100-024 | Shipped Complete | (#3) LTA/0298/2013 | Tools at Essner
50 | 148U9123-7 |  | SHIM, | 483-3-1050 | 747 | 1600 | 5 | Y | 4500051961 | 30 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes | 148U9123-7 | Shipped Complete | (#3) LTA/0298/2013 | Tools at Essner
51 | 140U2402-133 |  | WEB | 146U5312-17-02 | 747 | 1300 | 1 | Y | 4500051430 | 130 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes | 140U2402-133 | Shipped Complete | (#3) LTA/0298/2013 | Tools at Essner
52 | 140U2402-131 |  | WEB | 146U5312-17-02 | 747 | 1300 | 1 | Y | 4500051430 | 120 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes | 140U2402-131 | Shipped Complete | (#3) LTA/0298/2013 | Tools at Essner
53 | 182U0008-004 |  | SHIM, TAPERED | 906C2-813KIT | 747 | 1600 | 1 | Y | 4500051961 | 50 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013
54 | 148U9123-47 |  | SHIM, | 483-3-2051 | 747 | 1600 | 4 | Y | 4500051961 | 20 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013
55 | 145T2618-007 |  | SHIM | 145T2620-851-003 | 767 | 1800 | 5 | Y | 4500053424 | 90 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013
56 | 145T2618-005 |  | SHIM, | 145T2620-853-010 | 767 | 1800 | 2 | Y | 4500053424 | 50 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013
57 | 145T2618-004 |  | SHIM , | 145T2620-853-010 | 767 | 1800 | 2 | Y | 4500053424 | 30 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013
58 | 65B03629-080 |  | TEE, | 906C2-832KIT | 747 | 1600 | 1 | Y | 4500051919 | 30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | On Hold | 65B03629-080 | Parts are on HOLD per Brandy G. | (#11) LTA/0304/2013 | Tools at Essner
59 | 65B03637-027-500 |  | SHEAR TIE, | 906C1-729KIT | 747 | 1600 | 1 | Y | 4500051919 | 70 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | On Hold | 65B03637-027-500 | Parts are on HOLD per Brandy G. | (#11) LTA/0304/2013 | Tools at TAVAD shipping Dock
60 | 65B03629-079 |  | TEE, | 906C1-730KIT | 747 | 1600 | 1 | Y | 4500051919 | 20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | On Hold | 65B03629-079 | Parts are on HOLD per Brandy G. | (#11) LTA/0304/2013 | Tools at TAVAD shipping Dock
61 | 65B03630-101 |  | TEE, | 906C1-730KIT | 747 | 1600 | 1 | Y | 4500051919 | 60 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | On Hold |  | Parts are on HOLD per Brandy G. | (#11) LTA/0304/2013
62 | 65B03629-084 |  | TEE, | 906C2-830KIT | 747 | 1600 | 1 | Y | 4500051919 | 50 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | On Hold |  | Parts are on HOLD per Brandy G. | (#11) LTA/0304/2013
63 | 65B03629-083 |  | TEE, | 906C1-727KIT | 747 | 1600 | 1 | Y | 4500051919 | 40 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | On Hold |  | Parts are on HOLD per Brandy G. | (#11) LTA/0304/2013
64 | 65B03628-086 |  | SHEAR TIE, | 906C2-832KIT | 747 | 1600 | 1 | Y | 4500051919 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | On Hold |  | Parts are on HOLD per Brandy G. | (#11) LTA/0304/2013
65 | 65B02968-007 |  | FAIRING,SEAL | #N/A | 747 | 1600 | X | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Romoved from SOW / At Gamma as a -7-801 | (#9) LTA/0302/2013 | N/A
66 | 65B02886-007 |  | LONGERON - AUX | #N/A | 747 | 1600 | X | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Romoved from SOW / At Gamma as a -7-801 | (#9) LTA/0302/2013 | N/A
67 | 173U3512-3-03 |  | WEB, UPPER CHORD CLOSURE | #N/A | 747 | 1600 | X | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Removed from SOW / Metal Bond Assm / T-FW Supplier | (#9) LTA/0302/2013 | N/A
68 | 173U3512-3-02 |  | WEB, UPPER CHORD CLOSURE | #N/A | 747 | 1600 | X | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Removed from SOW / Detail Part to 173U3512-3-03 (below) / T-FW Supplier | (#9) LTA/0302/2013 | N/A
69 | 173U3502-5-02 |  | WEB, | #N/A | 747 | 1600 | X | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Rolled to 173U3502-12-01 (On FAI Plan) | (#9) LTA/0302/2013 | N/A
70 | 172U3053-1-02 |  | WEB, | #N/A | 747 | 1600 | X | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Removed from SOW / PAPO to XAIC | (#9) LTA/0302/2013 | N/A
71 | 148U3528-13-01 | 148U3528-15-01 | ANGLE, | #N/A | 747 | 1600 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Rolled / Sourced to LMI | (#9) LTA/0302/2013 | N/A
72 | 145T8760-187 |  | FILLER | #N/A | 767 | 1800 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Surplus Stock / No open Requirements | (#3) LTA/0298/2013 | N/A
73 | 145T8760-135 |  | FILLER TAPERED | 145T8796-801-002 | 767 | 1800 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Surplus Stock / No open Requirements | (#3) LTA/0298/2013 | N/A
74 | 145T8750-063 |  | SUPPORT BRACKET | #N/A | 767 | 1800 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | For L/U 1068 ONLY -/ Surplus Stock / No open Requirements | (#3) LTA/0298/2013 | N/A
Note on AI21: Jace Kline: The 65B04406-608 tools: DLT 4783526-00/C00 is being looked for and the FD 4881684-00/C00 is being utilized by another part. I do believe we can get Essner both of these tools within (2) weeks.
Note on AI31: Jace Kline: 6200891-00/C00 HB 6260997-00/C01 RB 6260998-00/C00 SUT

## SIR Status
Closed SIR's are hiden (column "G") | [12 empty] | 2022-08-22
SIR Number | Part Number | PO | Program | Submit Date | Submitter | Status | Completion Date | Priority | Age (in days) | SIR Responder | Supplier Question | TAT Response | Comments

## Stop Light Report
2022-08-22 |  |  |  |  | Issues & Status | [5 empty] | Package
0
Transition Project Manager
TGI Company Buyer | [10 empty] | Part Count
Receiving Supplier | [10 empty] | 20
Issue PO |  |  | 0% |  | Planning |  | 0%
Engr Data Received |  |  | 0% |  | Machine Start/Rough |  | 0%
Material Ordered |  |  | 0% |  | Machine Finish |  | 0% |  |  |  | Weekly Team Meetings
NC Program |  |  | 0% |  | Inspect |  | 0% |  |  |  | TBD
Date |  | Status Updates (Blue Text < 1 Week Old)
Sending Company
0
Receiving Company
| 0% |  | 0% | 0% |  | 0% |  | 0% |  | TBD
Going as planned
|  | Complete |  |  | In Progress |  |  |  | Not Started |  |  | Risk to plan
Behind plan
Production Line Status
Overall Transition Status
Transfer Initiated
Planning/ Programming
Processing and Assembly
FAI Submittal
FAI Delivery
Production
Transition

## Overall Performance
AutoScale Graph | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
Graph Date Range | 2019-06-28 | 2019-07-05 | 2019-07-12 | 2019-07-19 | 2019-07-26 | 2019-08-02 | 2019-08-09 | 2019-08-16 | 2019-08-23 | 2019-08-30 | 2019-09-06 | 2019-09-13 | 2019-09-20 | 2019-09-27 | 2019-10-04 | 2019-10-11 | 2019-10-18 | 2019-10-25 | 2019-11-01 | 2019-11-08 | 2019-11-15 | 2019-11-22 | 2019-11-29 | 2019-12-06 | 2019-12-13 | 2019-12-20 | 2019-12-27
Baseline FAI Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual FAIs Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## FAI Curve
AutoScale Graph | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Graph Date Range | 2018-06-01 | 2018-06-08 | 2018-06-15 | 2018-06-22 | 2018-06-29 | 2018-07-06 | 2018-07-13 | 2018-07-20 | 2018-07-27 | 2018-08-03 | 2018-08-10 | 2018-08-17 | 2018-08-24 | 2018-08-31 | 2018-09-07
Baseline FAI Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual FAIs Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Tool Transfer Curve
20-Point AutoScale Graph | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Graph Date Range | 2014-05-19 | 2014-05-26 01:16 | 2014-06-02 02:32 | 2014-06-09 03:47 | 2014-06-16 05:03 | 2014-06-23 06:19 | 2014-06-30 07:35 | 2014-07-07 08:51 | 2014-07-14 10:06 | 2014-07-21 11:22 | 2014-07-28 12:38 | 2014-08-04 13:54 | 2014-08-11 15:09 | 2014-08-18 16:25 | 2014-08-25 17:41 | 2014-09-01 18:57 | 2014-09-08 20:13 | 2014-09-15 21:28 | 2014-09-22 22:44 | 2014-09-30
Baseline Tools Transfer Plan | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 7 | 9 | 10
Actual Qty of Tools Transferred | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 5 | 7 | 10

## Transition Team RACI
Transition Team Roles and Responsibilities RACI
Key Transition Tasks | Support Team Members | [5 empty] | As Required
| Transition Project Manager | Corporate Procurement | TGI Company Procurement | Quality | Engineering | Grow Supplier | Exit Supplier | Governance/Compliance | Production Planning and Control
Release Purchase Order/LTA Addendum | A | I | R
Transmit Technical Data | A | I | I |  | R | I |  | C
Transfer Existing Tooling/Fixtures | A | I | R, I |  | R, I |  | C
Develop Line of Balance for Transition Parts with Agreed Overlap | A | I | C |  |  | I | C |  | R
Develop First Article Flow Plan | A | I | C | C | C | R | C
Order Raw Material | A | I | I |  |  | R
Procure New Tooling/Fixtures | A | I | R |  |  | R
Perform Initial Production Processses | A | I |  |  |  | R
Coordinate Outside Processing | A | I |  |  |  | R
Complete Production Processes | A | I |  |  |  | R
Prepare First Aritcle Insepction Package | A | I |  | C |  | R
Initiate Supplier Information Requests | C |  | I | I |  | A, R
Answer Supplier Information Requests | A | I |  | C | R | I
Approve First Article/Final Insepction | A | I | I | R | C | I
Transition Project Reporting | R | A | I | I |  | C
Support Team Members | Name |  | Phone |  | E-mail |  |  | Company Name
Project Manager
Corporate Procurement
TGI Company Procurement
TGI Company Procurement
Quality
Quality
Engineering
Engineering
New Supplier
RACI Definitions
(R)esponsible | (A)ccountable |  |  | (C)onsullted |  |  | (I)nformed
Group performing the activity | Group answerable for the activity and who holds yes/no authority |  |  | Group whose inputs and opinions are sought |  |  | Group kept up to date on decisions made

## Data Transmittal Checklist
TGI Transition Data Transmission Checksheet
Part
Sending TGI Company
| Name | Phone | E-mail | Street Address
Receiving Supplier Point of Contact
Task | TGI Task Lead | Available? Y (date) or N | Method of Transfer | Date Sent | Date Received
3D Models
2D Drawings
Mylars
Parts List / Indented Bill Of Materials
Notes List
Application List
Unique Raw Material Specifications
Unique Manufacturing Requirements
Unique Tooling Requirements
Special Processing Requirements
Links to approved special processing houses
Reference Planning
Unique Tooling/Fixtures/Gages/Test Equipment